## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Full Stack Development
INTERN NAME: | Ojas Patil
DOCUMENT NAME: | TEST PLAN
CREATED ON: | DD-MMM-YYYY
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | SkillConnect
PROJECT ID
INTERN NAME | Ojas Patil
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
SkillConnect is a comprehensive professional networking and job discovery platform built on the MERN stack (MongoDB, Express, React, Node.js). This Test Plan outlines the strategy to validate the functional correctness, performance, and usability of the application components including User Authentication, Job Board, Professional Feed, and Profile Management.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Functional Testing: 1. Authentication: Registration, Login, JWT handling, Protected Routes. 2. Job Module: Searching jobs, Filtering (by type/date), Applying (Modal). 3. Social Feed: Creating posts, fetching feed, linking to profiles. 4. Network: Sending/Accepting connection requests. Non-Functional Testing: 1. Responsiveness: UI layout on Mobile vs Desktop. 2. Basic Security: Password hashing, API authorization checks.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
1. Payment Gateway: No real payments are processed. 2. Load Testing: High-concurrency stress testing is out of scope for this MVP. 3. Native Mobile App: Testing is limited to Mobile Web Browsers. 4. Third-party Integrations: Real-time email delivery (mocked usually).
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
1. Zero Critical Bugs: High-severity issues blocking core flows (Login, Apply) must be resolved. 2. Functional Compliance: 100% of P1 requirements from the SRS must be implemented and verified. 3. Usability: The application must be intuitive and visually consistent (Glassmorphism theme).
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
1. QA Analyst / Tester (Self): Design test cases, execute manual tests, report bugs. 2. Developer (Self): Fix reported bugs, write unit tests. 3. Project Manager (Supervisor): Review deliverables and approve the final build.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
Agile/Iterative Testing: Testing will be conducted continuously as each feature is developed. Types of Testing: 1. Unit Testing: Verifying individual React components and API endpoints (Postman). 2. Integration Testing: Verifying data flow between Frontend and Backend. 3. System Testing: End-to-End validation of user journeys (e.g., Register -> Profile -> Apply).
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
1. Unit Testing: Verifying individual React components (e.g., Button, input validation) and API controller logic. 2. Integration Testing: Verifying communication between the React Frontend and Node.js Backend via REST APIs. 3. System Testing: Validating complete user workflows (e.g., A user registering, searching for a job, and applying) on the deployed Vercel environment.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Defect Severity & Priority: 1. Critical (P1): System crash, data corruption, or auth failure. Must fix immediately. 2. High (P2): Key functionality (e.g., Apply button) broken. Fix before next deploy. 3. Medium (P3): Minor functional error or CSS issue. Fix in next sprint. 4. Low (P4): Typos or cosmetic suggestions. Fix if time permits.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
1. All "In Scope" features have been tested. 2. 100% of P1 and P2 bugs are resolved. 3. User Acceptance Testing (UAT) is signed off (Self-verification).
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
1. Test Plan: This document. 2. Traceability Matrix: Excel sheet mapping functionalities to test cases. 3. Bug Reports: Log of issues found during testing (GitHub Issues or RAID log). 4. Test Summary Report: Final report summarizing test results (Pass/Fail rate).
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
1. Frameworks: Jest (Unit Testing), React Testing Library. 2. API Testing: Postman. 3. Browser Tools: Chrome DevTools (Network/Console/Responsive Mode). 4. Bug Tracking: GitHub Issues / RAID Log.
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Hardware: Standard Development Laptop (8GB+ RAM). Software: Google Chrome (Latest), Node.js v18+, MongoDB Compass. Network: Stable Broadband connection.
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Authentication System | Verify User Registration, Login (Valid/Invalid), Logout, and Token Persistence. | 2026-01-30 | 2026-01-31 | Self | PASS | Core flow working as expected.
User Profile Module | Verify Profile Creation, Editing Headline, Skills, and Experience details. | 2026-01-31 | 2026-02-01 | Self | PASS | Profile updates reflect immediately.
Job Board Features | Verify Job Listing, Search functionalities, Filtering logic, and Application flow (Modal). | 2026-02-01 | 2026-02-02 | Self | PASS | Filters work for Remote/Full-time.
Social Feed & Posts | Verify Post creation, image attachment (mock), Liking posts, and Feed rendering. | 2026-02-02 | 2026-02-02 | Self | PASS | Feed updates in real-time on post creation.
Networking Features | Verify Sending connection requests, Accepting/ignoring requests, and View Network page. | 2026-02-02 | 2026-02-03 | Self | PASS | Connection status syncs correctly.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.