## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | SkillConnect
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2025-12-29
EXPECTED COMPLETION DATE | 2026-01-31
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To develop a unified web platform that combines professional networking, job searching, and skill development into a single, cohesive user experience. The system will bridge the gap between education and employment by allowing users to showcase skills, connect with peers, and access learning resources.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Current platforms like LinkedIn and Coursera are fragmented. Students and professionals need to manage their network, job search, and learning in different places. SkillConnect solves this by integrating these pillars. It provides a "one-stop-shop" for career growth, increasing user engagement and reducing context switching. This project creates a portfolio-ready application demonstrating full-stack competence.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | 1. User Acquisition: Support 100+ concurrent users with sub-200ms response time. 2. Engagement: Users should be able to complete a "Job Application" flow in under 3 clicks. 3. Reliability: Achieve 99.9% uptime during the demo phase. 4. Completion: Deliver all core modules (Network, Jobs, Learning) by the project deadline.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Fully functional MERN Stack Web Application. 2. Source Code Repository (GitHub). 3. Technical Documentation (SRS, SDS, WBS). 4. User Manual and Installation Guide. 5. Final Project Report.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Functional Modules: - User Authentication (Login/Register) - Professional Feed (Posts, Likes) - Networking (Connect, Invites) - Job Board (Search, Apply, Save) - Learning Hub (Course Progress) - Messaging (Real-time Chat) Technical: - Responsive Web Design - RESTful API Development - Database Schema Design
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | - Native Mobile Applications (iOS/Android) - Payment Gateway Integration - live Video Streaming - Advanced AI/ML Job Matching Algorithms - Third-party API Integrations (e.g., LinkedIn Import)
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1. Lead Developer : Full Stack Development 2. Project Manager : Planning & Documentation 3. UI/UX Designer : Interface Design & Prototyping
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Mentor for guidance. - Online Documentation (React, Node.js docs). - Open Source Libraries (Tailwind, Mongoose).
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Total Budget: $0 - Development Tools (VS Code): Free - Hosting (Vercel/Render): Free Tier - Database (MongoDB Atlas): Free Tier - Design Tools (Figma): Free Tier
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Ojas Patil
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Project Supervisor/Mentor - Course Evaluators - Potential Employers/Recruiters (Target Audience) - Student Community
END CUSTOMER (Mention the client name.) | Job Seekers, Students, and Professionals looking to enhance their career and network.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. Time Constraint: High risk of feature creep impacting the deadline. 2. Technical Debt: Rapid development may lead to unoptimized code. 3. Data Loss: Risk of local database corruption (Mitigation: Use Cloud DB).
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | 1. Users have access to a modern web browser and internet connection. 2. Third-party libraries (e.g., Socket.io) will remain stable/compatible. 3. The free tier of hosting services will be sufficient for demo purposes.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 1. Timeline: Project must be completed by [End Date]. 2. Budget: Zero-budget project. 3. Tech Stack: Must strictly use MERN Stack as per requirements.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 01-04-2026 Completed SRS Document. User Requirements finalized.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 01-10-2026 WBS, Project Schedule, and RAID logs created.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 01-15-2026 Wireframes, UI Mockups, and Software Design Specification (SDS) approved.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 02-10-2026 Core modules (Auth, Feed, Jobs) coded and functioning.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 02-15-2026 System Testing performed. Test Plan & Reports submitted.
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 02-18-2026 Application deployed to Vercel/Render. Live URL generated
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 02-19-2026 Final Report, Code Handover, and Lessons Learnt Log submitted.