## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Progra 2023 - Full Stack Development Project Schedule
|  | PROJECT START DATE | 2025-12-29
|  | Display Week Sr No | 1 | [10 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2025-12-29 to 2026-03-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2025-12-29 to 2026-03-01
1 | Initiation | Project Setup |  |  |  |  | 2025-12-29 | 2025-12-31
1.1 |  | Define Scope | Create Project Charter |  | - | Self | 2025-12-29 | 2025-12-30 |  |  | Completed
1.2 |  | Environment | Install VS Code, Node.js |  | 1.1 | Self | 2025-12-30 | 2025-12-31 |  |  | Completed
2 | Planning | Requirements |  |  |  |  | 2026-01-01 | 2026-01-05 |  |  | Completed
2.1 |  | Documentation | Draft SRS |  | 1.2 | Self | 2026-01-01 | 2026-01-03 |  |  | Completed
2.2 |  | Architecture | Create WBS & Schedule |  | 2.1 | Self | 2026-01-04 | 2026-01-05 |  |  | Completed
3 | Design | UI/UX Design |  |  |  |  | 2026-01-06 | 2026-01-10 |  |  | Completed
3.1 |  | Database | Design MongoDB Schema | User, Job Models | 2.2 | Self | 2026-01-06 | 2026-01-07 |  |  | Completed
3.2 |  | Interface | UI Wireframing | Landing, Dashboard | 2.2 | Self | 2026-01-08 | 2026-01-10 |  |  | Completed
4 | Development | Frontend |  |  |  |  | 2026-01-11 | 2026-01-24 |  |  | Completed
4.1 |  | Setup | Init React + Vite | Tailwind Config | 3.2 | Self | 2026-01-11 | 2026-01-12 |  |  | Completed
4.2 |  | Components | Build Global Layout | Sidebar, Navbar | 4.1 | Self | 2026-01-13 | 2026-01-15 |  |  | Completed
4.3 |  | Pages | Connect & Jobs Pages | UI Implementation | 4.2 | Self | 2026-01-16 | 2026-01-19 |  |  | Completed
4.4 |  | Learn Module | Learning Hub | Course Cards | 4.3 | Self | 2026-01-20 | 2026-01-24 |  |  | Completed
|  | Learn Module | Learning Hub | Course Cards | 4.3 | Self |  |  |  |  | Completed
5 | Development | Backend |  |  |  |  | 2026-01-11 | 2026-01-24 |  |  | Completed
5.1 |  | Server | Setup Express App | Middleware, CORS | 3.1 | Self | 2026-01-11 | 2026-01-13 |  |  | Completed
5.2 |  | Auth | Auth Routes | JWT Implementation | 5.1 | Self | 2026-01-14 | 2026-01-17 |  |  | Completed
5.3 |  | API | Core Logic Routes | Jobs, Feed APIs | 5.2 | Self | 2026-01-18 | 2026-01-24 |  |  | Completed
6 | Integration | Full Stack |  |  |  |  | 2026-01-25 | 2026-01-29 |  |  | Completed
6.1 |  | API Connect | Fetch Data in React | Feed, Jobs Integration | 5.3 | Self | 2026-01-25 | 2026-01-27 |  |  | Completed
6.2 |  | Features | Job Filters & Search | Advanced Logic | 6.1 | Self | 2026-01-28 | 2026-01-29 |  |  | Completed
7 | Testing | QA |  |  |  |  | 2026-01-30 | 2026-02-01 |  |  | Completed
7.1 |  | Functional | Test All User Flows | Auth, Apply, Post | 6.2 | Self | 2026-01-30 | 2026-02-01 |  |  | Completed
8 | Closure | Wrap Up |  |  |  |  | 2026-02-02 | 2026-02-03 |  |  | Completed
8.1 |  | Docs | Final Report | Lessons Learned | 7.1 | Self | 2026-02-02 | 2026-02-03 |  |  | Completed
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1