## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Full Stack Development
INTERN NAME: | Ojas Patil
PROJECT NAME: | SkillConnect
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-02-13
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | SkillConnect |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Vinith Christopher
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2025-12-30 | Difficulty in managing complex state across React components. | Technical | Yes, Prop drilling became unmanageable. | Use Context API or Redux for global state management from the start. | Refactored User and Feed state to use React Context. | Self | Solved | significantly improved code readability.
2 | 2026-01-05 | Initial CSS styling was inconsistent and slow to develop. | Technical | Yes, mismatched padding/colors. | Adopt a utility-first CSS framework like Tailwind CSS. | Migrated from vanilla CSS to Tailwind CSS. | Self | Solved | Sped up UI development by 50%.
3 | 2026-01-10 | MongoDB connection timeouts during development. | Infrastructure | No | Implement proper error handling and connection pooling. | Updated Mongoose connection logic with retry strategies. | Self | Solved | -
4 | 2026-01-15 | "Profile Image Upload" significantly slowed down the server. | Performance | Yes, Server lag during upload. | Offload media storage to a dedicated CDN. | Integrated Cloudinary for image storage and optimization. | Self | Solved | Reduced server load.
5 | 2026-01-20 | Vercel deployment failed due to missing Environment Variables. | Deployment | Yes, Build logs showed 'undefined'. | Maintain a comprehensive .env.example and check deployment settings. | Added missing keys to Vercel dashboard. | Self | Solved | -
6 | 2026-01-25 | Git merge conflicts when working on multiple features. | Process | Yes | Use feature branches and merge into 'main' frequently. | Adopted Git Flow (Main -> Develop -> Feature Branch). | Self | Solved | -